MINUTES SKYPE MEETING YCEULSC.2008

Agenda

21:00 – 21:15	Reports: Sponsoring, PR, Recruitment, EU officials

21:15 – 21:30	PR coordination – transcript article, contact list, other media partners

21:30 - 	21:45	Idea collection: Recruitment

21:45 - 	22:00	Open issues

SHORT PLAN OUTLINE

Thomas

Update on Sponsoring

| Information | Comments | Decision |
| --- | --- | --- |
| Very slow progress, Thomas gets stuck with the secretaries. Some phone dates were cancelled. Two banks denied. Thomas sent information to Sanofi-Aventis. | Peter: Stay with it, we might succeed. It’s good practice. Also, ask the RSA group. | Thomas calls all the companies until the end of this week, asking if they are interested. |

Irina

Update on PR

| Information | Comments | Decision |
| --- | --- | --- |
| Irina has started establishing Media Contacts: |  |  |
| Ms. Kühr  We can supply an Article for the German transkript in December Flyer and invitation can be posted on www.biotechnologie.de | 2000 signs including spaces, a photo if possible Deadline: November 12th. Idea: Logo or Flyer as a picture Who is preparing a flyer? Irina can ask a friend but she’s not sure whether she’ll be available. Peter: We have drafts and old flyers from YEBN. The person who prepares the flyer can have them from Peter. | Irina sends Valentina the notes she took. Valentina will write an article for transkript until November 11th. Irina will forward the Article Peter asks Björn if there’s anyone in btS who is good at layout etc. Thomas will give the flyer a try. |
| We’ll also be added to the event calendar of the European Biotechnology News: http://www.biocom.de/biocom-verlag-gmbh/zeitschriften/ |  | Irina sends the corresponding information to Ms. Kühr. |
| Mr. Macht  Sent Irina contacts towards media and press  He suggests forwarding the information to the mailing list | Should we first select people and information? Peter: yes! First get in personal contact with the most important media, then, in December, send out the first press release. Irina: How to proceed? | Irina selects the most interesting media contacts and calls those people, asking for how they can help promote the event. Thomas forwards the information to naturejobs. |
| New Biotechnology Journal | Peter: We can have 1-page articles in the Journal | Valentina asks Deobra Keller for space in the NBJ. She puts Emilia in the CC: emilka.danilowicz@yebn.org |

Peter

Update Recruitment

| Information | Comments | Decision |
| --- | --- | --- |
| We need someone who makes sure that we reach all | Irina: We might also consider people outside btS  Annika or Sebastian. | Irina proposes the project at the next Meeting of btS Mainz Peter contacts Annika for PR IV Irina contacts Sebastian Olenyi to get hints for PR for the project |

Next Meeting: Monday, November 10th, 2008, 21.00