MINUTES SKYPE MEETING YCEULSC 01.12.2008

Agenda

21:00 - 21:15 Update Sponsoring, PR, Content, Team

21:15 - 21:30 Poster, Banner and announcement of the event

21:30 - 21:45 Task planning: Announcement of the conference, event organization, sponsoring

21:45 - 22:00 Offene Fragen

SHORT PLAN OUTLINE

Thomas

Update on Sponsoring

| Information | Comments | Decision |
| --- | --- | --- |
| Contact to Ms. Hautop (OmniLab) |  |  |
| Peter Lamken and Gregory von Abendroth are not listed on the btS eGroupware |  | Peter will send contact details to Thomas |
| Sanofi Aventis | No reply | Thomas to call again this week |
| Kelly Scientific – no contact information |  | Valentina mails contacts to Thomas |
| Kelly Scientific – no contact information |  | Valentina sends contact info |
| Replies from sponsors are pending | Peter: Suggestion to focus on most promising ones and insist to talk to people who decide. | Thomas will call the following companies and talk to decision makers in Sponsoring: Ernst&Young Sanofi-Aventis Invitrogen Fresenius VWR |

Irina and Valentina

Update on PR

| Information | Comments | Decision |
| --- | --- | --- |
| Article in transkript will not be printed in December but in January | Peter: We can write a new article in late December Maybe someone from BIOCOM can be present at the press conference? | Irina to ask Matthias when Ms. Kühr will be back to fix a small contribution for February 2009 and a half-to-one-page contribution for March 2009 |
| We can submit an article in Biotechnology (WILEY). It will be included in the forum | There seems to have been YEBN sections in the past. Deadline is Friday, Dec. 5th Either 200-300 words or 500 words with 2 small images | Valentina will write 200-300 words until Thursday morning and send it to Irina and Peter for proofreading. Irina to forward the article to WILEY (forgot the name of the lady…) |
| Nature Networks | There seem to be quite a lot of people. Irina suggests to establish | Valentina screens possibilities and reports back to the team. |
| Contact to Science | Debora Keller can provide a contact | Irina to ask Debora for the contact information. |
| New Biotechnology Journal Article was submitted by Valentina | We’re not sure when it will be published, probably January. |  |
| Press Release | We should spread a press release. Peter suggests to Irina to prepare a press info package Thomas: We should prepare the press conference very early Thomas suggests a web press conference. Thomas knows people who work in a studio that masters videos. | Irina will write a press release until Sunday and prepares a press info package. |

Peter

Recruitment

| Information | Comments | Decision |
| --- | --- | --- |
| We have a confirmation from Brussels | Mr. Sohail Luka, DG Research Other confirmations are coming slowly | Peter will contact him end of this week to set the frame for his contributions Peter is calling potential participants during this week |
| We are still missing 2 people: PR IV – Announce Conference Orga | Although there were several people interested, no new team member could be found on btS and YEBN meeting | Peter will talk to Valentin, Wenke and Sebastian and send an e-Mail to all YEBN AM 2008 participants. |

Peter

Content

| Information | Comments | Decision |
| --- | --- | --- |
| We have a blog! | Now: http://careersinlifesciences.wordpress.com/ Will be moved to: http://www.careersinlifesciences.btmag.eu/ | Sebastian is currently working on the Design. Luis to curate the Blog |
| We have a YouTube Channel: | http://www.youtube.com/user/YCEULSC | Sebastian will curate the YouTube account. Peter to send him login data |

All

Feedback on Poster, Banner and Text

| Information | Comments | Decision |
| --- | --- | --- |
| Poster | Emilia (before the meeting): I would increase font size, in particular the title, that this is a conference. What does Aegis mean? not clear and confusing. Would eliminate quotation marks. Would empasized the yebn.org website and deadline, somehow is lost at behind the "make the change! (happen..?) Peter: Should be in full page view when opened Thomas: Maybe we can add a map of Europe Valentina: Text should be bigger Write Patron instead of Aegis | Peter to implement changes |
| Banner | Banner B is most appealing, but Banner A is more catchy Irina: Put a blue Frame around Banner B. | Peter to implement changes and send banner as .jpg and .eps file to Irina and Valentina |
| Texts | No coorections Valentina: Ask members to translate to their mother tongue. Thomas: Ask people if they have central internal mailing lists for their institutes and universities. They can work very well to spread the word | Peter to call chairs during this week to ask them to translate and distribute the information Peter to recruit one member oversee the mailings. |

Next Meeting: Monday, December 8th, 2008, 21.00