##### Action Plan

| Year 1: October 2007-September 2008 | Semester 1 |  |  |  |  |  | Semester 2 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 10/07 | 11/07 | 12/07 | 1/ 08 | 2/ 08 | 3/ 08 | 4/ 08 | 5/ 08 | 6/ 08 | 7/ 08 | 8/ 08 | 9/ 08 |  |
| Activity Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Implementing body |
| Activity 1: project coordination; 1-1 steering and management |  |  |  |  |  |  |  |  |  |  |  |  | Steering Com. HUB |
| Activity 1: project coordination; 1-2 kick-off WS; preparation |  |  |  |  |  |  |  |  |  |  |  |  | HAU HUB |
| Activity 1: project coordination; 1-2 kick-off WS and further meetings; workshop |  |  |  |  |  |  |  |  |  |  |  |  | HAU HUB |
| Activity 1: project coordination; 1-2 kick-off WS and further meetings; yearly meetings |  |  |  |  |  |  |  |  |  |  |  |  | Steering Committee |
| Activity 1: project coordination; 1-3 project monitoring and evaluation |  |  |  |  |  |  |  |  |  |  |  |  | Steering Com. HUB |
| Activity 2: sandwich programme; phase A; preparation |  |  |  |  |  |  |  |  |  |  |  |  | KULEUVEN |
| Activity 2: sandwich programme; phase A; implementation |  |  |  |  |  |  |  |  |  |  |  |  | Europ.partners KULEUVEN |
| Activity 2: sandwich programme; phase A; follow-up |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2: sandwich programme; phase B; preparation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2: sandwich programme; phase B; implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2: sandwich programme; phase B; follow-up |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3 : summer schools ; 3-1 Summer School A; preparation |  |  |  |  |  |  |  |  |  |  |  |  | HUB |
| Activity 3 : summer schools ; 3-1 Summer School A; implementation |  |  |  |  |  |  |  |  |  |  |  |  | HUB |
| Activity 3 : summer schools ; 3-1 Summer School A; follow-up |  |  |  |  |  |  |  |  |  |  |  |  | HUB Steering Com. |
| Activity 3 : summer schools ; 3-2 Summer School B; preparation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3 : summer schools ; 3-2 Summer School B; implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3 : summer schools ; 3-2 Summer School B; follow-up |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3 : summer schools ; 3-3 Summer School C; preparation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3 : summer schools ; 3-3 Summer School C; implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3 : summer schools ; 3-3 Summer School C; follow-up |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 4 : modules ; team work |  |  |  |  |  |  |  |  |  |  |  |  | CAU module teams |
| Activity 4 : modules ; team meetings |  |  |  |  |  |  |  |  |  |  |  |  | CAU module teams |
| Activity 4 : modules ; test implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 4 : modules ; evaluation and incorporation |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Year 1 | Semester 1 |  |  |  |  |  | Semester 2 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity Month | 10/07 | 11/07 | 12/07 | 1/ 08 | 2/ 08 | 3/ 08 | 4/ 08 | 5/ 08 | 6/ 08 | 7/ 08 | 8/ 08 | 9/ 08 | Implementing body |
| Activity 5 : university-industry network ; 5-4 coordination desks ; preparation desk officer training |  |  |  |  |  |  |  |  |  |  |  |  | HUB SLU |
| Activity 5 : university-industry network ; 5-4 coordination desks ; desk officer training |  |  |  |  |  |  |  |  |  |  |  |  | HUB SLU |
| Activity 5 : university-industry network ; 5-4 coordination desks ; desk set-up, round table meetings, networking activities |  |  |  |  |  |  |  |  |  |  |  |  | Asian partners SLU |
| Activity 5 : university-industry network ; 5-4 coordination desks ; stakeholder meetings |  |  |  |  |  |  |  |  |  |  |  |  | Asian partners SLU |
| Activity 5 : university-industry network ; 5-4 coordination desks ; transfer to own responsibility |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 5 : university-industry network ; 5-1 study projects ; preparation first round |  |  |  |  |  |  |  |  |  |  |  |  | HAU, SLU Asian partners |
| Activity 5 : university-industry network ; 5-1 study projects ; implementation first round |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 5 : university-industry network ; 5-1 study projects ; follow-up first round |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 5 : university-industry network ; 5-1 study projects ; preparation second round |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 5 : university-industry network ; 5-1 study projects ; implementation second round |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 5 : university-industry network ; 5-1 study projects ; follow-up second round |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 5 : university-industry network ; 5-1 study projects ; transfer to own responsibility |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 5 : university-industry network ; 5-2 internships ; preparation first round |  |  |  |  |  |  |  |  |  |  |  |  | CAU, SLU Asian partners |
| Activity 5 : university-industry network ; 5-2 internships ; implementation first round |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 5 : university-industry network ; 5-2 internships ; follow-up first round |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 5 : university-industry network ; 5-2 internships ; preparation second round |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 5 : university-industry network ; 5-2 internships ; implementation second round |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 5 : university-industry network ; 5-2 internships ; follow-up second round |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 5 : university-industry network ; 5-2 internships ; transfer to own responsibility |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 5 : university-industry network ; 5-3 mentoring ; preparation procedures and networking |  |  |  |  |  |  |  |  |  |  |  |  | UNSYIAH SLU Asian partners |
| Activity 5 : university-industry network ; 5-3 mentoring ; starting meeting |  |  |  |  |  |  |  |  |  |  |  |  | Asian partners |
| Activity 5 : university-industry network ; 5-3 mentoring ; pairs |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 5 : university-industry network ; 5-3 mentoring ; evaluations |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 6 : curriculum evaluation; team meetings |  |  |  |  |  |  |  |  |  |  |  |  | KVL EvaluationTeam |
| Activity 6 : curriculum evaluation; preparation |  |  |  |  |  |  |  |  |  |  |  |  | KVL EvaluationTeam |
| Activity 6 : curriculum evaluation; incorporation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 6 : curriculum evaluation ; follow-up |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 7 : internet site ; set-up |  |  |  |  |  |  |  |  |  |  |  |  | HUB |
| Activity 7 : internet site ; maintenance |  |  |  |  |  |  |  |  |  |  |  |  | HUB |

| For the following years: October, 2008 – September, 2010 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | 10/2008 -3//2009 | 4/2009 – 9/2009 | 10/2009 – 3/2010 | 4/2010 – 9/2010 |  |
| Activity | Semester 3 | 4 | 5 | 6 | Implementing body |
| Activity 1: project coordination; 1-1 steering and management |  |  |  |  | Steering Com. HUB |
| Activity 1: project coordination; 1-2 kick-off WS and further meetings; yearly meetings |  | Month 23 |  | Month 35 | HUB/SLU HUB/UNSYIAH |
| Activity 1: project coordination; 1-3 project monitoring and evaluation |  |  |  | and after | SteeringCom. HUB, external |
| Activity 2: sandwich programme; phase A; implementation |  | until month 22 |  |  | Europ.partners KULEUVEN |
| Activity 2: sandwich programme; phase A; follow-up |  | Month 23 |  |  | KULEUVEN SteeringCom. |
| Activity 2: sandwich programme; phase B; preparation |  | Months 21-23 |  |  | KULeuven |
| Activity 2: sandwich programme; phase B; implementation |  |  | Months 24-35 |  | Europ.partners KULeuven |
| Activity 2: sandwich programme; phase B; follow-up |  |  |  | Month 36 | KULeuven SteeringCom. |
| Activity 3 : summer schools ; 3-2 Summer School B; preparation |  | Months 19-22 |  |  | SLU |
| Activity 3 : summer schools ; 3-2 Summer School B; implementation |  | Month 23 |  |  | SLU |
| Activity 3 : summer schools ; 3-2 Summer School B; follow-up |  | Month 24 |  |  | SLU SteeringCom. |
| Activity 3 : summer schools ; 3-3 Summer School C; preparation |  |  |  | Month 30-34 | UNSYIAH |
| Activity 3 : summer schools ; 3-3 Summer School C; implementation |  |  |  | Month 35 | UNSYIAH |
| Activity 3 : summer schools ; 3-3 Summer School C; follow-up |  |  |  | Month 36 | UNSYIAH SteeringCom. |
| Activity 4 : modules ; team work | Until month 15 |  |  |  | CAU module teams |
| Activity 4 : modules ; team meetings |  | Month 23 |  | Month 35 | CAU module teams |
| Activity 4 : modules ; test implementation | Month 18-23 |  |  |  | CAU module teams |
| Activity 4 : modules ; evaluation and incorporation |  |  | From month 24 | and beyond | Asian partners CAU |
| Activity 5 : university-industry network ; 5-4 coordination desks ; desk set-up, round table meetings, networking activities |  | Until month 22 |  |  | Asian partners SLU |
| Activity 5 : university-industry network ; 5-4 coordination desks ; stakeholder meeting 2 |  | Month 23 |  |  | Asian partners SLU |
| Activity 5 : university-industry network ; 5-4 coordination desks ; transfer to own responsibility |  |  | From month 24-36 | and after | Asian partners SLU |
| Activity 5 : university-industry network ; 5-1 study projects ; preparation first round | Months 13-16 |  |  |  | HAU Asian partners SLU |
| Activity 5 : university-industry network ; 5-1 study projects ; implementation first round | Months 17-21 |  |  |  | HAU Asian partners SLU |
| Activity 5 : university-industry network ; 5-1 study projects ; follow-up first round |  | Month 22 |  |  | Asian partners SteeringCom. |
| Activity 5 : university-industry network ; 5-1 study projects ; preparation second round |  | Months 22-23 |  |  | HAU Asian partners SLU |
| Activity 5 : university-industry network ; 5-1 study projects ; implementation second round |  |  | Months 24-28 |  | HAU Asian partners SLU |
| Activity 5 : university-industry network ; 5-1 study projects ; follow-up second round |  |  | month 29 |  | Asian partners SteeringCom. |
| Activity 5 : university-industry network ; 5-1 study projects ; transfer to own responsibility |  |  |  | and beyond | HAU Asian partners SLU |
| Activity 5 : university-industry network ; 5-2 internships ; preparation first round | Months 12-16 |  |  |  | CAU Asian partners |
| Activity 5 : university-industry network ; 5-2 internships ; implementation first round | Month 17-21 |  |  |  | CAU Asian partners |
| Activity 5 : university-industry network ; 5-2 internships ; follow-up first round |  | Month 22 |  |  | Asian partners SteeringCom. |
| Activity 5 : university-industry network ; 5-2 internships ; preparation second round |  | Months 21-23 |  |  | CAU Asian partners |
| Activity 5 : university-industry network ; 5-2 internships ; implementation second round |  |  | Months 24-28 |  | CAU Asian partners |
| Activity 5 : university-industry network ; 5-2 internships ; follow-up second round |  |  | Month 29 |  | Asian partners SteeringCom. |
| Activity 5 : university-industry network ; 5-2 internships ; transfer to own responsibility |  |  |  | and beyond | CAU Asian partners |
| Activity 5 : university-industry network ; 5-3 mentoring ; pairs |  |  |  | and beyond | UNSYIAH Asian partners |
| Activity 5 : university-industry network ; 5-3 mentoring ; evaluations | Month 17 |  | Month 29 |  | Asian partners UNSYIAH |
| Activity 6 : curriculum evaluation; team meetings |  | Month 23 |  | Month 35 | KVL EvaluationTeam |
| Activity 6 : curriculum evaluation ; preparation |  |  |  |  | KVL EvaluationTeam |
| Activity 6 : curriculum evaluation ; incorporation |  |  |  |  | KVL Asian partners EvaluationTeam |
| Activity 6 : curriculum evaluation ; follow-up |  |  |  | Months 34-35 | KVL Asian partners SteeringCom. |
| Activity 7 : internet site ; maintenance |  |  |  | and beyond | HUB |