| Number | Activity |  | Participants |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Define Project Scope |  | Customer/EI QCI |  |  |
|  | Define Organizational Structure (titles & job desc) |  | Customer/EI QCI |  |  |
|  | Define documentation platforms/control structure |  | Customer/EI QCI |  |  |
|  | EI QCI Provide Agreement for Professional Services |  | Customer/EI QCI |  |  |
|  | Establish POA&M/Deliver |  | Customer/EI QCI |  |  |
|  | EI QCI Provide ANSI/ISO/ASQ Q9000-2000 STDl |  | EI QCI |  |  |
|  | EI QCI Provide Draft Quality Manual |  | EI QCI |  |  |
|  | Contact Registrar for Formal Assessment Date |  | EI QCI |  |  |
|  | Review/Draft of QM01 |  | Customer |  |  |
|  | Define, develop and draft QP |  | EI QCI |  |  |
|  | Define, develop and draft DFCs |  | EI QCI |  |  |
|  | Define, develop and draft PAWs |  | EI QCI |  |  |
|  | Review Draft's of QP/DFC/PAW |  | Customer |  |  |
|  | Define, develop and write draft Quality Related Forms |  | EI QCI |  |  |
|  | Prep ISO Training Materials |  | EI QCI |  |  |
|  | Conduct ISO 9001 Project Mgmt Overview |  | Customer/EI QCI |  |  |
|  | Conduct ISO 9001 Requirements Training |  | Customer/EI QCI |  |  |
|  | Formalize Document Control |  | Customer/EI QCI |  |  |
|  | Review/incorporate initial draft inputs received to formal QMS |  | Customer/EI QCI |  |  |
|  | Conduct Management review of all developed QMS documentation |  | Customer/EI QCI |  |  |
|  | Incoporate changes from Management Review |  | Customer |  |  |
|  | Distribute revised documentation for approval |  | Customer |  |  |
|  | Review all final drafts |  | Customer/EI QCI |  |  |
|  | Rev.1 procedures approved, published & distributed |  | Customer |  |  |
|  | Submit QMS to Registrar for review and approval |  | Customer/EI QCI |  |  |
|  | Develop Master Document Control List/Files |  | Customer/EI QCI |  |  |
|  | Implement procedures/self audit |  | Customer |  |  |
|  | Prep Internal Auditor Training Materials |  | EI QCI |  |  |
|  | Conduct Internal Auditor Training |  | Customer/EI QCI |  |  |
|  | Schedule internal audits |  | Customer/EI QCI |  |  |
|  | Conduct Internal audits |  | Customer/EI QCI |  |  |
|  | Corrective actions developed and implemented |  | Customer |  |  |
|  | Effectiveness of corrective actions verified |  | Customer/EI QCI |  |  |
|  | Conduct Management review meetings |  | Customer/EI QCI |  |  |
|  | ISO 9001 Awareness/Audit Preparation Training |  | Customer/EI QCI |  |  |
|  | Formal assessment is conducted by the Registrar |  | Customer/EI QCI |  |  |
|  | Corrective Action is submitted to the Registrar |  | Customer/EI QCI |  |  |