C3M Project Activities and Timetable

## Phase				Activities				 Time Frame				Lead Team Members

| ### Phase 1 – The Team | ● Work with LHS Tech Support to download Cmap Tools ● Provide summary of concept mapping research and introductory materials to Gimble and Newkirk ● Draft Cmap Tools Manual for LHS Educators ● Meetings (2 days) for: Intro to Cmap Tools Collaboration on evaluation design Developing strategy for Fall Classroom applications | July-August 2006 July-August 2006 July-August 2006 July-August 2006 July-August 2006 | Jane Heinze-Fry Jane Heinze-Fry Jane Heinze-Fry Jane Heinze-Fry, Barbara Newkirk, Elliott Gimble Jane Heinze-Fry, Barbara Newkirk, Elliott Gimble |
| --- | --- | --- | --- |
| ### Phase 2 – The Students | ● Develop first unit concept map ● Pre-unit Planning Meetings (2) ● Evaluation/Next Steps Meetings (2) ● Implementation/Class Visits (2) ● Develop second unit concept map | September 2006 September 2006/January 2007 October, 2006/February 2007 October, 2006/February 2007 January 2006 | Jane Heinze-Fry Jane Heinze-Fry, Barbara Newkirk, Elliott Gimble Jane Heinze-Fry, Barbara Newkirk, Elliott Gimble Jane Heinze-Fry B. Newkirk, E. Gimble |
| ### Phase 3 – The Report | ● Consolidate and analyze data, draw conclusions, revise (as necessary) Manual, write final report | February – April, 2007 | Jane Heinze-Fry |
| ### Phase 4 – The Sharing | ● Plan and implement 2-hour teacher training | April – May, 2007 | B. Newkirk, E. Gimble |