Project Proposal

Project Name:		Concept Mapping

Proposed by:			Joe Nicholls

Board Owner:		Hugh Beedie

External Sponsor:		n/a

Project Manager:		Joe Nicholls

Date:				January 2005

Project Description

Description, objectives and scope: - Setup and trial concept mapping client and server software - Develop and run tutorial sessions - Develop training and support documentation - Make recommendations for ongoing service provision Project will be carried out principally by Joe Nicholls, future engage TEG staff engaged part-time across all sections within INSRV The outcome will be a report recommended approach and toolset for performing Concept Mapping.

Exclusions:

Strategic Alignment

Indicate how the project will give benefit under one or more of the following headings:

Research (RAE):

Learning & Teaching (TQA):

Staff / Student Experience:

Corporate administration / Efficiency and effectiveness:

Third Mission / All Wales:

Audit / Contingency Planning / Legal:

Resources

Financial Resources: Project capital requirements with dates and budget: n/a Recurrent cost added: Recurrent cost saved:

Staff Resources: Key project staff and/or skills: Joe Nicholls (UFG) Ongoing staff / maintenance effort added: 0.1 FTE technical support Ongoing staff / maintenance effort saved:

Any other potential resource issues? None

Timescale / Constraints

Preferred start date: Jan 2005 Estimated Duration: 9 months – Jan 2005 until Oct 2005 Deadlines or other time constraints: Report to be submitted to INSRV Board by end of Oct 2005

Future work that depends on this project: The methodology and technology has proven to be of value across all forms of endeavour in higher education organisations.

Prerequisites or issues not noted elsewhere: Dependent on gaining sufficient access to INSRV staff time

| Outline Plan |  |  |  |  |
| --- | --- | --- | --- | --- |
| Task/Milestone | Duration | Start* | End* | Comments |
| Install and setup Cmap server and CmapTools client on network desktop | 1 month | 1st Jan | 31st Jan |  |
| Submit bid to University Learning and Teaching Innovation programme | 2 weeks | 1st Feb |  |  |
| Raise awareness and promote potential value of concept mapping and associated collaborative tools | 6 months | 1st Feb |  |  |
| Develop training and support documentation, workshops and associated resources | 4 months | 1st Feb |  |  |
| Evaluation – obtain feedback from established users | 2 months | 1st Aug | 30th Sept |  |

*give relative times e.g. week1, week2 etc if start date not known.